## TASK_LIST
| RFC 45341 | For Archival Year 2018 - Archival Date 08/08/2020 |  |  |  | START
| Tasks /JOBS | Description | Comments / Changes before start | Change? | ST | Date | Time | RUNTIME
A | Code Change | Implement programming changes - See Tab" 2109 Changes" | Implement Package SZHPCHG0045341P1 | Yes | C | 2020-01-27
0 | Notification | Update operation's calendar. Set-up comunations e-mail Notify QDB team about archive run date | No Need. RFC will do. Opended CTASK0034047 for Client Support Openned CTASK0034016 for QDB team |  | C | 2020-07-30
1 | EDIT | Update ISDSZ1.P.PARMS card for current archival year | R720A & M910C - change YR=18 M935C - change year = 11 ( 10 year period) | Yes | C | 2019-12-09
2 | TEST RUN | Run SZANNUAL netwark schedule on Test Machine | TASK0085031 REQ0102429 to start on 01/16/2019 |  | C | 2020-08-06
3 | SZANNUAL | Send request to Set Annual run schedule for Saturday, August 8, 2020 | Send Network change request to Job Scheduling team TASK0156342 |  | C | 2020-08-04
4 | SPUFI | ISDSZ0.T.DB2.SQL(ARCHIVET) | Run before archival process to count entries for year 2016 |  | C | 2020-08-08
5 | SZ0#R720 | SATISFACTORY ACADEMIC PROGRESS | ISDSZ1.P.PARMS(R720A) - see Task # 1 |  | C | 2020-08-08 | 02.21.51 | 0.14
6 | SZ0#W01X | WEEKLY FULL IMAGE COPY OF ALL SZ0 TABLES BEFORE REORG |  |  | C | 2020-08-08 | 02.22.00 | 0.63
7 | SZ0#M91A | FAM YEAR-END ARCHIVE OF STUDENTS | ISDSZ1.P.PARMS(M910C) - see Task # 1 BEG-SID=000000000,END-SID=100000000 |  | C | 2020-08-08 | 02.22.39 | 68.79
8 | SZ0#M91B |  | BEG-SID=100000000,END-SID=200000000 |  | C | 2020-08-08 | 03.31.26 | 37.62
9 | SZ0#M91C | FAM YEAR-END ARCHIVE OF STUDENTS |  |  | C | 2020-08-08 | 04.09.04 | 28.71
10 | SZ0#M91D | FAM YEAR-END ARCHIVE OF STUDENTS |  |  | C | 2020-08-08 | 04.37.47 | 27.31
11 | SZ0#M91E | FAM YEAR-END ARCHIVE OF STUDENTS |  |  | C | 2020-08-08 | 05.05.06 | 25.89
12 | SZ0#M91F | FAM YEAR-END ARCHIVE OF STUDENTS |  |  | C | 2020-08-08 | 05.31.00 | 27.52
13 | SZ0#M91G | FAM YEAR-END ARCHIVE OF STUDENTS |  |  | C | 2020-08-08 | 05.58.32 | 25.97
14 | SZ0#M91H | FAM YEAR-END ARCHIVE OF STUDENTS |  |  | C | 2020-08-08 | 06.24.32 | 24.41
15 | SZ0#M91I | FAM YEAR-END ARCHIVE OF STUDENTS |  |  | C | 2020-08-08 | 06.48.58 | 23.84
16 | SZ0#M91J | FAM YEAR-END ARCHIVE OF STUDENTS | BEG-SID=900000000,END-SID=999999999 |  | C | 2020-08-08 | 07.12.50 | 22.14
17 | SZ0#M91K | FAM YEAR-END ARCHIVE OF FUND FILE | ISDSZ1.P.PARMS(M935C) - See Task # 1 |  | C | 2020-08-08 | 07.34.59 | 0.12
18 | SZ0#M911 | MERGE YEAR-END ARCHIVE TRANSACTIONS |  |  | C | 2020-08-08 | 07.35.10 | 5.54
19 | SZ0#M912 | GENERATE YEAR-END ARCHIVE AND FUND TOTAL RDS REPORT |  |  | C | 2020-08-08 | 07.40.42 | 6.15
20 | SZ0#M925 | Delete Orhpan records before M930. |  |  | C | 2020-08-08 | 07.46.52 | 0.86
21 | SZ0#M930 | Deletes locator records |  |  | C | 2020-08-08 | 07.47.45 | 3.24
22 | SZ0#W01A | START FAM DB2 DATABASE FOR UTILITIES ONLY |  |  | C | 2020-08-08 | 07:51
23 | SZ0#W01B | WEEKLY REORGANIZATION, IMAGE AND RUNSTATS OF SA TABLESPACES |  |  | C | 2020-08-08 | 07:51
24 | SZ0#W01F | START FAM DATABASE FOR READ/WRITE ACCESS AFTER DB2 MAINTENANCE |  |  | C | 2020-08-08 | 07:51
25 | SZ0#W01G | REBIND FAM PRODUCTION CICS PACKAGES |  |  | C | 2020-08-08 | 07:51
26 | SZ0#W01H | REBIND FAM PRODUCTION BATCH PLANS - station 40 |  |  | C | 2020-08-08 | 07:51
27 | SZ0#W01H | REBIND FAM PRODUCTION BATCH PLANS - station 50 |  |  | C | 2020-08-08 | 07:51
28 | SZ0#Q100 | GENERATE LOAD FILE FOR FA QDB - FA_STU_PROFILE |  |  | C | 2020-08-08 | 07.51.57 | 6.26
29 | SZ0#Q110 | GENERATE LOAD FILE FOR FA QDB - FA_STU_COLL_MAJ/FA_STU_YEAR |  |  | C | 2020-08-08 | 07.51.57 | 6.77
30 | SZ0#Q120 | GENERATE LOAD FILE FOR FA QDB - FA_STU_TERM |  |  | C | 2020-08-08 | 07.51.57 | 3.7
31 | SZ0#Q121 | FTP END-FILE TO SERVER |  |  | C | 2020-08-08 | 07.58.44 | 0.04
32 | SPUFI | ISDSZ0.T.DB2.SQL(ARCHIVET) | Run after archival process to count entries left after year 2014 archival. Check results. Prepare the final report. | No orphan | C | 2020-08-08
33 | SPUFI | SRHP0.SQLLIB.PROD(ARCHIVE2) | Identify Orphan entries In the FAM tables | N/A | C
34 | SPUFI | ISDSZ0.T.JCL(SZ0#ORPH) | Run the job to delete orphan entries - After updated srudent's list | N/A
On Request
| SZ0#M913 | ARCHIVE INDIVIDUAL STUDENTS | Not Applicable

## Production_run_stats
| FAM DB2 Tables in Archive and Enties | Year | Before Archive Jobs | After Main Archive jobs | After Orhan records and FAM locater table purge | Comments
1 | SZ0_FAM_AGGR | 99 | 2182481 | 2182481 |  | Not part of archival process
2 | SZ0_FAM_LOCATOR | 18 | 65950 | 38470 |  | Deleted by SZ0M930 - no FAM interest SL_IND is set to 'N' on AAFILE
3 | SZ0_STU_LOCATOR | 99 | 353743 | 326257
4 | SZ0_AID_PACKGNG | 18 | 81274
5 | SZ0_FMLY_R_CALC | 18 | 53648
6 | SZ0_FMLY_RESOUR | 18 | 53648
7 | SZ0_INSTIT_BDGT | 18 | 53854
8 | SZ0_PELL_GRANT | 18 | 50795
9 | SZ0_STUDENT_AID | 18 | 65940
10 | SZ0_AWD_DISB | 18 | 2511912
11 | SZ0_AWD_PERIOD | 18 | 310748
12 | SZ0_AWD_TRAN | 18 | 1385056
13 | SZ0_FAM_AWARD | 18 | 308056
14 | SZ0_FAM_STU_AID | 18 | 47000
15 | SZ0_STU_AID_TRK | 18 | 184468
16 | SZ0_ELEC_LOAN | 18 | 15414
17 | SZ0_ELEC_LOAN_APP | 18 | 31122
18 | SZ0_LOAN | 18 | 15430
19 | SZ0_LOAN_DISB_HIST | 18 | 78065
20 | SZ0_STU_LOAN | 18 | 30742
21 | SZ0_GRANT_DISB_HIST | 18 | 36347
22 | SZ0_EPAL_AWD | 18 | 18833
23 | SZ0_EPAL_AWD_DTL | 18 | 91228
24 | SZ0_SAP_SUMMARY | 18 | 216352
25 | SZ0_SAP_DETAIL | 18 | 392360
26 | SZ0_AUDIT_DETL | 18 | 3434324 | 608
27 | SZ0_CORE_AUDIT | 18 | 1100021 | 608
28 | SZ0_LOAN_BORROWER | 18 | 6701
29 | SZ0_FUND | 99 | 34475 | 34475 |  | Not part of archival process
30 | SZ0_FUND_NOTE | 99 | 1527 | 1527 |  | Not part of archival process
31 | SZ0_FISC_YR_ACT | 99 | 207738 | 207738
32 | SZ0MCS | 18 | 15903 |  |  | Deleted by SZ0#M925 as orphen entry
33 | SZ0_AWD_WSP | 18 | 9948
34 | SZ0_UNEX_ATTR | 18 | 1693 | 1693 |  | Not part of archival process
35 | SZ0_ECSI_INTERFACE | 99 | 33429 | 33429 |  | Not part of archival process
36 | SZ0_LOAN_INTVW | 99 | 65165 | 65164 |  | Deleted by SZ0#M925 as orphen entry
37 | SZ0_BUD_CRITERIA | 18 | 554 | 554
38 | SZ0_PELL_INDEX | 18 | 35 | 0
39 | SZ0_CAL_GRANT_CEIL | 18 | 35 | 0

## Archive_info_PROD
| FAM Tables to be archived | Archive Year | Segemnt | Arch ID | Report | Report Order | New order | Image of Screen
0 | [5 empty] | @
1 | SZ0_FAM_AGGR | 99 | SLFILE | SL | n/a | C
2 | SZ0_FAM_LOCATOR | 18 | SLFILE | SL | n/a | C
3 | SZ0_STU_LOCATOR | 99 | SLFILE | SL | n/a | C
4 | SZ0_AID_PACKGNG | 18 | SAFILE | SA | Award Year - NEEDS ANALYSIS DATA | D
5 | SZ0_FMLY_R_CALC | 18 | SAFILE | SA | Award Year - NEEDS ANALYSIS DATA | D |  | 325
6 | SZ0_FMLY_RESOUR | 18 | SAFILE | SA | Award Year - NEEDS ANALYSIS DATA | D |  | 312
7 | SZ0_INSTIT_BDGT | 18 | SAFILE | SA | Award Year - NEEDS ANALYSIS DATA | D
8 | SZ0_PELL_GRANT | 18 | SAFILE | SA | Award Year - PELL DATA | D |  | 38X
9 | SZ0_STUDENT_AID | 18 | SAFILE | SA | Award Year - NEEDS ANALYSIS DATA | D
10 | SZ0_AWD_DISB | 18 | SWFILE | SW | AWARD SUMMARY | E
11 | SZ0_AWD_PERIOD | 18 | SWFILE | SW | AWARD SUMMARY | E |  | 319
12 | SZ0_AWD_TRAN | 18 | SWFILE | SW | AWARD SUMMARY | E |  | 320
13 | SZ0_FAM_AWARD | 18 | SWFILE | SW | AWARD SUMMARY / Award Detail | E
14 | SZ0_FAM_STU_AID | 18 | STFILE | ST |  | F
15 | SZ0_STU_AID_TRK | 18 | STFILE | ST | DOCUMENT TRACKING | F |  | 306
16 | SZ0_ELEC_LOAN | 18 | SSFILE | SS | DIRECT LOAN DATA | G |  | 391
17 | SZ0_ELEC_LOAN_APP | 18 | SSFILE | SS |  | G |  | 393
18 | SZ0_LOAN | 18 | SGFILE | SG | LOAN PAYMENT DATA | G |  | 33A
19 | SZ0_LOAN_DISB_HIST | 18 |  | EH | DIRECT LOAN DISB | G |  | 392
20 | SZ0_STU_LOAN | 18 | SGFILE | SG | LOAN PAYMENT DATA | G |  | 33A
21 | SZ0_GRANT_DISB_HIST | 18 |  | GD | PELL GRANT DISBURSMENT HISTORY DATA | H |  | 38H
22 | SZ0_EPAL | 18 |  | EP |  | J |  | 380
23 | SZ0_EPAL_DTL | 18 |  | EP |  | J |  | 380
24 | SZ0_SAP_SUMMARY ( PROC_YR) | 18 |  | SP |  | K |  | 3SP
25 | SZ0_SAP_DETAIL (PROC_YR) | 18 |  | SP |  | K |  | 3SP
26 | SZ0_AUDIT_DETL | 18 | AUFILE | AU | AUDIT DATA | X |  | 349
27 | SZ0_CORE_AUDIT | 18 | AUFILE | AU | AUDIT DATA | X |  | 349
28 | SZ0_LOAN_BORROWER | 18 |  | EB | n/a
29 | SZ0_FUND | 7 | SFFILE | SF | n/a |  |  | 331
30 | SZ0_FUND_NOTE | 7 | SFFILE | SF | n/a
31 | SZ0_FISC_YR_ACT | 2011
32 | SZ0MCS | 18 |  | MI | Middle Income Scholarship | L |  | 3MS
33 | SZ0_AWD_WSP | 18 |  | WO
38 | SZ0_PELL_INDEX | 18
39 | SZ0_CAL_GRANT_CEIL | 18
Tables will / may be archived in the future
34 | SZ0_UNEX_ATTR |  |  | UX | 3UX displays history. |  | M | 3UX
35 | SZ0_ECSI_INTERFACE | 99 |  |  | Keep for 10 year?
37 | SZ0_BUD_CRITERIA
Tables may need cleanup
36 | SZ0_LOAN_INTVW |  |  |  | Done in SZ0#M925
Additional New Table
| SZ0_WSP_APPRVR_INFO | N/A |  |  | Refershed daily
| SZ0_WSP_HIRE_INFO | N/A |  |  | Refershed daily
Additional data copied to the archive dataset
| ANECDOTAL DATA |  |  | AM | ANECDOTAL DATA = ??? | I | I
| NAME |  |  | AA | DEMOGRAPHIC AND ADDRESS DATA -name | A | A
| ADDRESS |  |  | AD | DEMOGRAPHIC AND ADDRESS DATA -addr | A | A

## DB2_tables
FAM TABLES participating in Archival process
| DB2 Tables | Archive? | Comments | Oldest entry
1.01 | SZ0_AID_PACKGNG | Yes
1.02 | SZ0_AUDIT_DETL | Yes
1.03 | SZ0_AWD_DISB | Yes
1.04 | SZ0_AWD_PERIOD | Yes
1.05 | SZ0_AWD_TRAN | Yes
1.06 | SZ0_CORE_AUDIT | Yes
1.07 | SZ0_ELEC_LOAN | Yes
1.08 | SZ0_ELEC_LOAN_APP | Yes
1.09 | SZ0_FAM_AGGR | Yes | IF AGGR_AMT and AGGR_YEAR_CNT = 0 . There are 8800+ rows in the table that do not have SZ0_FAM_LOCATOR table. | 1990 - for NO FAM locator
1.1 | SZ0_FAM_AWARD | Yes
1.11 | SZ0_FAM_LOCATOR | Yes | If no Active Records in SZ0_FAM_AGGR
1.12 | SZ0_FAM_STU_AID | Yes
1.13 | SZ0_FISC_YR_ACT | Yes | FUND control amounts - Not a Student specific table. information kept for 10 years.
1.14 | SZ0_FMLY_R_CALC | Yes
1.15 | SZ0_FMLY_RESOUR | Yes
1.16 | SZ0_FUND | N | Reported with SZ0_FISC_YR_ACT table report
1.17 | SZ0_FUND_NOTE | N
1.18 | SZ0_GRANT_DISB_HIST | Yes
1.19 | SZ0_INSTIT_BDGT | Yes
1.2 | SZ0_LOAN | Yes
1.21 | SZ0_LOAN_BORROWER | Yes
1.22 | SZ0_LOAN_DISB_HIST | Yes
1.23 | SZ0_PELL_GRANT | Yes
1.24 | SZ0_STU_AID_TRK | Yes
1.25 | SZ0_STU_LOAN | Yes
1.26 | SZ0_STU_LOCATOR | Yes | If no Active Records in SZ0_FAM_AGGR
1.27 | SZ0_STUDENT_AID | Yes
1.28 | SZ0_EPAL_AWD | Yes | Starting 2014 Archival process - delete 2013 data | 2013
1.29 | SZ0_EPAL_AWD_DTL | Yes | Starting 2014 Archival process | 2013
1.3 | SZ0_SAP_DETAIL | Yes | Starting 2014 Process year archival process | 1967-2014
1.31 | SZ0_SAP_SUMMARY | Yes | Starting 2014 Process year archival process | 1967-2014
2.01 | SZ0MCS | Yes | Starting 2018 archival process | 2015
2.02 | SZ0_AWD_WSP | Yes | Starting 2019 | 2017
3.01 | SZ0_UNEX_ATTR |  | Under review
4.01 | SZ0_LOAN_INTVW | Delete no loan enties | Delete not used entries. Not a year specific - but needs cleanup, to prevent abend when deleting SZ0_STU_LOCATOR entries
FAM TABLES Updated annualy
5.01 | SZ0_PELL_INDEX | Update | Based on user input | 2014
5.02 | SZ0_CAL_GRANT_CEILING | Update | Based on user input | 2011
FAM TABLES NOT participating in Archival process
6.01 | SZ0_BUD_CRITERIA | NO
6.02 | SZ0_CENSUS_ATTR | NO | SAP uses this table
6.03 | SZ0_EDUS_CUM | NO
6.04 | SZ0_EXCLUDE_UID | NO
6.05 | SZ0_FAM_TERM_CONV | NO | FAM Admin Group - Not a student specific table
6.06 | SZ0_INTVW_AGGR_AREA | NO
6.07 | SZ0_INTVW_LOAN_TYPE | NO
6.08 | SZ0_MAX_TERM_OVRD | NO | DBT2 IS empty. No access to DB2P
6.09 | SZ0_NOSSN | NO |  | 2015
6.1 | SZ0_PKG_EDIT_CTL | NO | control totals for the last two years
6.11 | SZ0_PROC_OUTPUT | NO
6.12 | SZ0_RESTART | NO
6.13 | SZ0_SAP_MAX_UNITS | NO | Control file from 11A thru 15A
6.14 | SZ0_STU_ACAD_SUPL | NO | Not a year specific
6.15 | SZ0_STU_BUD | NO | Budget codes and total amount per term and Budget code. Not a student specific. Starting 05A thru 15A
6.16 | SZ0_STU_LOCATOR | NO
6.17 | SZ0_STU_MAX_TERM_OVRD | NO | To be reviewed later | 2015
6.18 | SZ0AIS_FRPRHIST | NO | Earn Paid Amount by TERM - never archived
FAM TABLES May be obsolete
7.01 | SZ0_SAP_DETAIL_OLD | N/A | Is this obsolete ? | 1971 - 2012
7.02 | SZ0_SAP_SUMMARY_OLD | N/A | I do not have access to the table - is this obsolete ? Entries up to 2012 | 1971 - 2012
7.03 | SZ0_LOAN_ORIG | NO | Only Years 92-95. DB2T is empty | 1992- 1995

## 2019 Changes
| Report format |  | Program changes
Screens
| 306 |  | SZSBA910 | update SZ0_AWD_WSP table changes
325
|  |  | SZ0M915 | Update 306 and325 screen changed
|  |  | SZ0WSPRC | copybook for SZ0_AWD_WSP | in production
DB2 table |  |  |  | SZ0_PELL_INDEX
SZ0_CAL_GRANT_CEILING
REQ0074636
TASK0085091
CTASK0034016
REQ0074636
SZSCSARC |  | ISDSYE.T.T.SS.COBCOPY |  | Summer units EST and Actual | 20NOV19
SIACFIBW |  | ISDSYE.T.T.SS.COBCOPY |  | OK | 30OCT19
SZEPRC |  | ISDDCL.P.DM0.COB.COPYLIB |  |  | 23OCT19
SZSCSLRC |  | ISDDCL.P.DM0.COB.COPYLIB |  | SL-CNSLR-ID , SL-DEPEN-BIRTH-DT | 23OCT19
SR0SMTIN |  | ISDDCL.P.DM0.COB.COPYLIB |  |  | 26JUN19
SZSCSARC |  |  |  | SA-PK-TRK-STA2-DT
SA-PK-TRK-STAT-DT
SAD56 - trk stat on or before year 20
SAD56 vERF stat SAD55 - TRK-Stat after 20

## Future_changed
FMLY_RESOUR
STU_IRS_SCHD1_CD CHARACTER(1)
PAR_IRS_SCHD1_CD CHARACTER(1)
AID_PACKGNG
R46188 10 RNWL-OTHER-FUND
SIS_ELEC_LOAN_APP
INFRMD_BRWR_CMPLT_FL
INFRMD_BRWR_CMPLT_DT